## APQM Gantt
APQM system
|  |  | Period Highlight: |  | 127 |  |  |  | Plan |  |  | Actual |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
Ordered by Actual Start. LMD: 1/30/2014 |  |  | PLAN | PLAN | ACTUAL | ACTUAL | PERCENT | time axis 2013-10-08 to 2014-02-16
CATEGORY | PRIORITY | ACTIVITY | START | DURATION | START | DURATION | COMPLETE | 2013-10-08: PERIODS
[8 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | 85 | 86 | 87 | 88 | 89 | 90 | 91 | 92 | 93 | 94 | 95 | 96 | 97 | 98 | 99 | 100 | 101 | 102 | 103 | 104 | 105 | 106 | 107 | 108 | 109 | 110 | 111 | 112 | 113 | 114 | 115 | 116 | 117 | 118 | 119 | 120 | 121 | 122 | 123 | 124 | 125 | 126 | 127 | 128 | 129 | 130 | 131 | 132
SIF | 5 | Import SIFs from “Sales Database”. | 1 | 3 | 1 | 4 | 100%
All | 3 | Format fields (Numbers align to right, alphanumeric to left, etc). | 30 | 1 | 1 | 2 | 100% | bar: PERIODS 88
BOM | 5 | Import BOMs from “Sales Database”. | 3 | 1 | 3 | 2 | 100%
SIF | 4 | Show in SIF form only fields necessaries. | 16 | 1 | 3 | 1 | 100%
SIF | 5 | Filter in importer |  |  | 7 | 2 | 100%
System | 4 | Integrity with transactions. | 17 | 2 | 8 | 2 | 100% | bar: PERIODS 18; PERIODS 81
BOM | 4 | Add field for each BOM line to check mark if line item is a "Directed Buy". | 4 | 1 | 10 | 1 | 100%
SIF | 4 | Add field with buyer's name on SIF assigned by. | 15 | 1 | 10 | 2 | 100% | bar: PERIODS 91
BOM | 3 | Status Field: Q=Quote, E:Estimate, P=Pass thru, M=Manufacturing Item, Firm requirement. | 30 | 1 | 11 | 1 | 100%
BOM |  | Enable edit BOM Line. Adding fields: VendorQuoteEst, PurchasingComments, SalesComments |  |  | 14 | 2 | 100%
System |  | Validator resource complete |  |  | 16 | 1 | 100%
BOM |  | Validator improved, showing message in field with error. Fields added to BOM Line CapComAssm, LeadTimePPAP. BOM Form improved. |  |  | 17 | 1 | 100%
RFQ |  | Improved RFQ Detail list as a single table. Showing only items with status equal to COMPLETED when selecting a BOM Line. |  |  | 21 | 1 | 100%
RFQ Summary | 4 | Hand Total A (Vendor), Total B (Logistics-Freight Cost) and Total C (Unknown) in RFQ Summary | 14 | 2 | 22 | 2 | 100%
RFQ Summary |  | RFQ Summary calculating total done. |  |  | 24 | 1 | 100%
SIF | 3 | Update SIF information after selecting Vendor's RFQ. Edited: Import SIF Detail from Sales DB | 23 | 1 | 25 | 1 | 100%
RFQ | 4 | RFQ Number generated with SIF number and then a sequential number. | 4 | 1 | 28 | 2 | 100%
RFQ | 4 | Add these fields when sending new RFQ: Revision Level, Volume (EAU) | 7 | 1 | 29 | 1 | 100%
RFQ | 4 | Optional Target Price instead of Cost. | 7 | 2 | 29 | 2 | 100%
RFQ | 3 | EAU in RFQ. | 29 | 1 | 29 | 1 | 100%
|  | Fields added to RFQ, BOM, BOMHeader, Item Master. |  |  | 31 | 1 | 100%
System |  | Notifier control developed. Control Chosen in Jquery for dropdowns. |  |  | 32 | 2 | 100%
Supplier |  | Fast Supplier create from Send New RFQ, Prompt user control implemented, Fields added to RFQCountPerBomLine |  |  | 35 | 2 | 100%
RFQ | 4 | Enable option for Vendor for no quote (Status will change to Declined) add reason field. | 14 | 1 | 36 | 1 | 100%
System |  | Warning the user when javascript is disabled |  |  | 37 | 1 | 100%
RFQ |  | Handling javascript when it is not enabled on client, Adding fields to RFQ: CommentsToVendor, UMWeight, SIFHeaderKey |  |  | 38 | 1 | 100%
BOM |  | Be able to add new items to Market Sector done. Importing market sector from sales db |  |  | 39 | 1 | 100%
Reports |  | HTML Report for sales able to export to excel |  |  | 39 | 1 | 100%
Reports |  | HTML Sales Report completed; System's Status for BOMLine working, Fixing XML Connections with OnInit Event. |  |  | 42 | 2 | 100%
System |  | Logout in menu |  |  | 44 | 1 | 100%
System | 2 | Develop a Login system. | 44 | 3 | 44 | 2 | 100%
RFQ | 4 | Multiple Attachments in RFQ. | 8 | 3 | 46 | 5 | 100%
Reports |  | Add Material Position to Sales Report and BOM Lines |  |  | 51 | 1 | 100%
Reports |  | Flag line for no quote in sales report |  |  | 51 | 1 | 100%
BOM |  | Progress indicator in BOM; To be able to change the BOM Line status. |  |  | 51 | 1 | 100%
RFQ |  | Selected status before Awarded for RFQs. Set award manually. |  |  | 51 | 2 | 100% | bar: PERIODS 57
RFQ Summary |  | Persisting RFQSummary including columns order; Status, Sequence added to RFQSummary; |  |  | 52 | 5 | 100%
Reports |  | TotalMaterialCost and TotalCostReduction calculated and added to ReportToSales |  |  | 58 | 1 | 100%
Reports |  | LeadTimePPAP and Tooling Cost added to ReportToSales |  |  | 59 | 1 | 100%
RFQ |  | Instructions in RFQ with Intro.js plugin |  |  | 60 | 2 | 100% | bar: PERIODS 67
RFQ |  | Edit RFQ line. Calculating formulas in RFQ when entering a new line. |  |  | 63 | 1 | 100%
RFQ |  | Attachments in RFQ from Vendor to Capsonic done. Change Password form complete. |  |  | 64 | 2 | 100%
RFQ |  | Fix display marketsector in rfq. Imported status for BOM. Logo Changed. |  |  | 66 | 2 | 100%
RFQ | 3 | Be able to choose several vendors to email about one part number. | 24 | 1 | 67 | 4 | 100%
BOM |  | Multiple EAU in BOM Line, this will create one RFQ per EAU specified. |  |  | 71 | 1 | 100%
RFQ |  | EAV field added to RFQ. Validation for Email integrated. |  |  | 72 | 1 | 100%
Supplier |  | Import Vendors catalog to APQM |  | 1 | 73 | 1 | 100%
SIF |  | Define directories for place SalesDB2APQM.exe in Elgin and Auburn Hills |  | 1 | 74 | 1 | 100%
Supplier |  | Fields handle excusively by buyer added to Supplier entity. |  |  | 81 | 1 | 100%
System |  | Validating list of numbers delimited by comma. (EAU in BOM) |  |  | 81 | 1 | 100%
System | 3 | Relationships in database. | 21 | 1 | 87 | 1 | 100%
System | 3 | Show descriptive messages when throwing errors | 21 | 1 | 88 | 1 | 100%
System | 1 | Add control calendar for each date field. | 49 | 1 | 88 | 1 | 100%
System |  | Disable directory listing and redirect to Default.aspx |  | 1 | 88 | 1 | 100%
All |  | Assign BOM, SIF, RFQ to a Buyer. |  |  | 88 | 4 | 100%
System |  | Toggle Views |  | 2 | 91 | 1 | 100%
BOM |  | Add status information box for BOM Lines |  | 1 | 91 | 1 | 100%
All |  | Filter lists by Buyer: RFQ, SIF |  |  | 91 | 3 | 100%
RFQ | 4 | Optional Button when sending new request: Aero or Auto. | 14 | 1 |  | 1 | 100%
All | 3 | Allow filtering data by these part numbers: Finished Good (From BOM), Capsonic PN (From BOM), Manufacture PN(From drawingos or BOM) | 35 | 1 |  | 2 | 100%
Re-schedule or New:
BOM | 3 | Filter BOM list by Buyer | 94 | 1 | 94 | 1 | 100%
Supplier | 3 | Content inside emails for Vendors. | 94 | 1 | 94 | 1 | 100%
RFQ | 3 | Choose vendor filtering by its Commodity. | 94 | 1 | 94 | 5 | 100%
BOM | 3 | Calculate EAU for BOM automatically, pulled from SIF | 95 | 1 | 98 | 1 | 100%
System | 3 | Standardize names | 95 | 1 | 99 | 1 | 100%
SIF | 3 | Create SIF Detail | 95 | 1 | 106 | 1 | 100%
All | 3 | Validate forms. | 95 | 1 | 14 | 3 | 90% | bar: PERIODS 14 to PERIODS 15
RFQ | 3 | Multiple Part Numbers to RFQ, handle manufacture P/N and Capsonic P/N columns | 98 | 2
RFQ | 1 | Implement expiration RFQs functionality. (Due date, close, blocked, extend them). | 100 | 1
Supplier | 3 | Ranking functionality. | 101 | 2
Reports | 3 | Develop all reports. Begin with necessaries and in HTML format. | 105 | 5
System | 1 | User's Manual | 119 | 5
System | 1 | Technical Documentation | 126 | 5
New after using the system:
| 5 | Handle compatibility view in Internet Explorer |  |  | 99 | 1 | 100%
| 5 | Re-order steps of instructions in RFQ after standardization and movement of some fields location. |  |  | 99 | 1 | 100%
| 5 | Report to Sales is not shwoing all BOM lines |  |  | 100 | 1 | 100%
| 5 | Change Dissmised to No Quote |  |  | 100 | 1 | 100%
| 5 | Buyer should be able to update RFQ |  |  | 100 | 1 | 100%
| 5 | Delete RFQ |  |  | 101 | 1 | 100%
| 5 | Force EAU field to be filled in so Purchasing cannot send out RFQ without EAUs |  |  | 101 | 1 | 100%
| 5 | Status of BOM Line should be change to In Progress when RFQ(s) are sent. |  |  | 101 | 1 | 100%
| 4 | RFQ Summary: Pull Total Cost for update it in BOM Line. |  |  | 102 | 1 | 100%
| 4 | Allow Buyers to create manually RFQ (without submitting to Vendor) |  |  | 102 | 1 | 100%
| 4 | Add column for know if SIF was created or imported |  |  | 105 | 1 | 100%
| 3 | Add titles along the different screens |  |  | 105 | 1 | 100%
| 3 | Hide Cost field in BOM |  |  | 105 | 1 | 100%
| 1 | Remove BOMDetailKey when selecting a BOM Line in RFQSummary |  |  | 105 | 1 | 100%
| 1 | Remove columns from Suppliers list (Manuf. Loc., Ship Loc., Quoted Currency) |  |  | 105 | 1 | 100%
| 1 | Remove title Proyected Annual Volume when sending new RFQ |  |  | 105 | 1 | 100%
| 1 | Prevent overlapping in RFQ Summary with columns and Header info. |  |  | 106 | 1 | 100%
| 3 | Not apply automatically EAU for all BOM lines when they have been processed |  |  | 107 | 1 | 100%
| 3 | Pull Tooling field from RFQ to RFQ summary. |  |  | 107 | 1 | 100%
| 2 | Prevent from exit a page every time we save something |  |  | 107 | 6 | 100%
| 2 | Remove Multiview controls, instead, use normal webpages. |  |  | 107 | 6 | 100%
| 3 | RFQs inside BOM |  |  | 109 | 15 | 100%
| 1 | Re-sent RFQ |  |  | 113 | 1 | 100%
|  | Add last date send column for RFQs |  |  | 114 | 1 | 100%
| 3 | Add cavitation and material fields to RFQ Form. |  |  | 114 | 1 | 100%
|  | Allow to change Vendor's email when resending RFQ. |  |  | 115 | 1 | 100%
| 1 | Delete BOM from SIF list. | 116 | 1 | 116 | 1 | 100%
|  | Remove EAU validation from BOM Form |  |  | 120 | 1 | 100%
| 3 | Use utiliy of SalesDB for import data from APQM
Change BOM Component status when its RFQ award/selected has been deleted
|  | Allow edit RFQ about Buyers fields. |  | 2 | 123 | 5 | 80%
New Lead Times requested by Seth.
| 2 | Add Prototype Tooling and Prototype quantity to RFQ Summary (by Martha) | 116 | 1
| 3 | Do not allow a vendor to fill out a survey more than once.
Tasks that will be treated as improvements. (After system's basics work)
| 2 | Use FS Commodities.
| 2 | Draft when sending a RFQ.
| 1 | Status Progress as column in SIF list. | 116 | 1
System | 1 | Static Headers for Tables | 112 | 1
System | 1 | Style webpage. | 113 | 4 |  |  | 50%
Open RFQs from RFQ summary
| 3 | Leyend when sending RFQ depending id Aerospacial or Automotive
Add Buyer contact that created an RFQ inside email
See issue with NDA
Page inside emails
Note on Q13: Transactions in SalesDB2APQM done.
Note on AA13: Transactions in RFQ Form done.
Note on CL13: Transactions done for APQM
Note on DK104: Designed for allow 5 RFQs
Note on DX109: Holyday

## Issues
APQM Issues
# | Date | Creator | Issue | Status | Solution | Open
1 | 2013-10-16 | Lorie Bergelin | Cannot open SalesDB2APQM.exe from her location. | Closed | MS Access does not support x64, therefore I had to compile the solution for x86 | In Progress
2 | [5 empty] | On Hold
3 | [5 empty] | Closed
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100
101
102
103
104
105
106
107
108
109
110
111
112
113
114
115
116
117
118
119
120
121
122
123
124
125
126
127
128
129
130
131
132
133
134
135
136
137
138
139
140
141
142
143
144
145
146
147
148
149
150
151
152
153
154
155
156
157
158
159
160
161
162
163
164
165
166
167
168
169
170
171
172
173
174
175
176
177
178
179
180
181
182
183
184
185
186
187
188
189
190
191
192
193
194
195
196
197
198
199
200
201
202
203
204
205
206
207
208
209
210
211
212
213
214
215
216
217
218
219
220
221
222
223
224
225
226
227
228
229
230
231
232
233
234