## APQM Gantt
APQM system
|  |  | Period Highlight: |  | 268 |  |  |  | Plan |  |  | Actual |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
Ordered by Actual Start. LMD: 7/1/2014 |  |  | PLAN | PLAN | ACTUAL | ACTUAL | PERCENT | time axis 2013-10-08 to 2014-08-17
CATEGORY | PRIORITY | ACTIVITY | START | DURATION | START | DURATION | COMPLETE | 2013-10-08: PERIODS
[8 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | 85 | 86 | 87 | 88 | 89 | 90 | 91 | 92 | 93 | 94 | 95 | 96 | 97 | 98 | 99 | 100 | 101 | 102 | 103 | 104 | 105 | 106 | 107 | 108 | 109 | 110 | 111 | 112 | 113 | 114 | 115 | 116 | 117 | 118 | 119 | 120 | 121 | 122 | 123 | 124 | 125 | 126 | 127 | 128 | 129 | 130 | 131 | 132 | 133 | 134 | 135 | 136 | 137 | 138 | 139 | 140 | 141 | 142 | 143 | 144 | 145 | 146 | 147 | 148 | 149 | 150 | 151 | 152 | 153 | 154 | 155 | 156 | 157 | 158 | 159 | 160 | 161 | 162 | 163 | 164 | 165 | 166 | 167 | 168 | 169 | 170 | 171 | 172 | 173 | 174 | 175 | 176 | 177 | 178 | 179 | 180 | 181 | 182 | 183 | 184 | 185 | 186 | 187 | 188 | 189 | 190 | 191 | 192 | 193 | 194 | 195 | 196 | 197 | 198 | 199 | 200 | 201 | 202 | 203 | 204 | 205 | 206 | 207 | 208 | 209 | 210 | 211 | 212 | 213 | 214 | 215 | 216 | 217 | 218 | 219 | 220 | 221 | 222 | 223 | 224 | 225 | 226 | 227 | 228 | 229 | 230 | 231 | 232 | 233 | 234 | 235 | 236 | 237 | 238 | 239 | 240 | 241 | 242 | 243 | 244 | 245 | 246 | 247 | 248 | 249 | 250 | 251 | 252 | 253 | 254 | 255 | 256 | 257 | 258 | 259 | 260 | 261 | 262 | 263 | 264 | 265 | 266 | 267 | 268 | 269 | 270 | 271 | 272 | 273 | 274 | 275 | 276 | 277 | 278 | 279 | 280 | 281 | 282 | 283 | 284 | 285 | 286 | 287 | 288 | 289 | 290 | 291 | 292 | 293 | 294 | 295 | 296 | 297 | 298 | 299 | 300 | 301 | 302 | 303 | 304 | 305 | 306 | 307 | 308 | 309 | 310 | 311 | 312 | 313 | 314
SIF | 5 | Import SIFs from “Sales Database”. | 1 | 3 | 1 | 4 | 100%
All | 3 | Format fields (Numbers align to right, alphanumeric to left, etc). | 30 | 1 | 1 | 2 | 100% | bar: PERIODS 88
BOM | 5 | Import BOMs from “Sales Database”. | 3 | 1 | 3 | 2 | 100%
SIF | 4 | Show in SIF form only fields necessaries. | 16 | 1 | 3 | 1 | 100%
SIF | 5 | Filter in importer |  |  | 7 | 2 | 100%
System | 4 | Integrity with transactions. | 17 | 2 | 8 | 2 | 100% | bar: PERIODS 18; PERIODS 81
BOM | 4 | Add field for each BOM line to check mark if line item is a "Directed Buy". | 4 | 1 | 10 | 1 | 100%
SIF | 4 | Add field with buyer's name on SIF assigned by. | 15 | 1 | 10 | 2 | 100% | bar: PERIODS 91
BOM | 3 | Status Field: Q=Quote, E:Estimate, P=Pass thru, M=Manufacturing Item, Firm requirement. | 30 | 1 | 11 | 1 | 100%
BOM |  | Enable edit BOM Line. Adding fields: VendorQuoteEst, PurchasingComments, SalesComments |  |  | 14 | 2 | 100%
System |  | Validator resource complete |  |  | 16 | 1 | 100%
BOM |  | Validator improved, showing message in field with error. Fields added to BOM Line CapComAssm, LeadTimePPAP. BOM Form improved. |  |  | 17 | 1 | 100%
RFQ |  | Improved RFQ Detail list as a single table. Showing only items with status equal to COMPLETED when selecting a BOM Line. |  |  | 21 | 1 | 100%
RFQ Summary | 4 | Hand Total A (Vendor), Total B (Logistics-Freight Cost) and Total C (Unknown) in RFQ Summary | 14 | 2 | 22 | 2 | 100%
RFQ Summary |  | RFQ Summary calculating total done. |  |  | 24 | 1 | 100%
SIF | 3 | Update SIF information after selecting Vendor's RFQ. Edited: Import SIF Detail from Sales DB | 23 | 1 | 25 | 1 | 100%
RFQ | 4 | RFQ Number generated with SIF number and then a sequential number. | 4 | 1 | 28 | 2 | 100%
RFQ | 4 | Add these fields when sending new RFQ: Revision Level, Volume (EAU) | 7 | 1 | 29 | 1 | 100%
RFQ | 4 | Optional Target Price instead of Cost. | 7 | 2 | 29 | 2 | 100%
RFQ | 3 | EAU in RFQ. | 29 | 1 | 29 | 1 | 100%
|  | Fields added to RFQ, BOM, BOMHeader, Item Master. |  |  | 31 | 1 | 100%
System |  | Notifier control developed. Control Chosen in Jquery for dropdowns. |  |  | 32 | 2 | 100%
Supplier |  | Fast Supplier create from Send New RFQ, Prompt user control implemented, Fields added to RFQCountPerBomLine |  |  | 35 | 2 | 100%
RFQ | 4 | Enable option for Vendor for no quote (Status will change to Declined) add reason field. | 14 | 1 | 36 | 1 | 100%
System |  | Warning the user when javascript is disabled |  |  | 37 | 1 | 100%
RFQ |  | Handling javascript when it is not enabled on client, Adding fields to RFQ: CommentsToVendor, UMWeight, SIFHeaderKey |  |  | 38 | 1 | 100%
BOM |  | Be able to add new items to Market Sector done. Importing market sector from sales db |  |  | 39 | 1 | 100%
Reports |  | HTML Report for sales able to export to excel |  |  | 39 | 1 | 100%
Reports |  | HTML Sales Report completed; System's Status for BOMLine working, Fixing XML Connections with OnInit Event. |  |  | 42 | 2 | 100%
System |  | Logout in menu |  |  | 44 | 1 | 100%
System | 2 | Develop a Login system. | 44 | 3 | 44 | 2 | 100%
RFQ | 4 | Multiple Attachments in RFQ. | 8 | 3 | 46 | 5 | 100%
Reports |  | Add Material Position to Sales Report and BOM Lines |  |  | 51 | 1 | 100%
Reports |  | Flag line for no quote in sales report |  |  | 51 | 1 | 100%
BOM |  | Progress indicator in BOM; To be able to change the BOM Line status. |  |  | 51 | 1 | 100%
RFQ |  | Selected status before Awarded for RFQs. Set award manually. |  |  | 51 | 2 | 100% | bar: PERIODS 57
RFQ Summary |  | Persisting RFQSummary including columns order; Status, Sequence added to RFQSummary; |  |  | 52 | 5 | 100%
Reports |  | TotalMaterialCost and TotalCostReduction calculated and added to ReportToSales |  |  | 58 | 1 | 100%
Reports |  | LeadTimePPAP and Tooling Cost added to ReportToSales |  |  | 59 | 1 | 100%
RFQ |  | Instructions in RFQ with Intro.js plugin |  |  | 60 | 2 | 100% | bar: PERIODS 67
RFQ |  | Edit RFQ line. Calculating formulas in RFQ when entering a new line. |  |  | 63 | 1 | 100%
RFQ |  | Attachments in RFQ from Vendor to Capsonic done. Change Password form complete. |  |  | 64 | 2 | 100%
RFQ |  | Fix display marketsector in rfq. Imported status for BOM. Logo Changed. |  |  | 66 | 2 | 100%
RFQ | 3 | Be able to choose several vendors to email about one part number. | 24 | 1 | 67 | 4 | 100%
BOM |  | Multiple EAU in BOM Line, this will create one RFQ per EAU specified. |  |  | 71 | 1 | 100%
RFQ |  | EAV field added to RFQ. Validation for Email integrated. |  |  | 72 | 1 | 100%
Supplier |  | Import Vendors catalog to APQM |  | 1 | 73 | 1 | 100%
SIF |  | Define directories for place SalesDB2APQM.exe in Elgin and Auburn Hills |  | 1 | 74 | 1 | 100%
Supplier |  | Fields handle excusively by buyer added to Supplier entity. |  |  | 81 | 1 | 100%
System |  | Validating list of numbers delimited by comma. (EAU in BOM) |  |  | 81 | 1 | 100%
System | 3 | Relationships in database. | 21 | 1 | 87 | 1 | 100%
System | 3 | Show descriptive messages when throwing errors | 21 | 1 | 88 | 1 | 100%
System | 1 | Add control calendar for each date field. | 49 | 1 | 88 | 1 | 100%
System |  | Disable directory listing and redirect to Default.aspx |  | 1 | 88 | 1 | 100%
All |  | Assign BOM, SIF, RFQ to a Buyer. |  |  | 88 | 4 | 100%
System |  | Toggle Views |  | 2 | 91 | 1 | 100%
BOM |  | Add status information box for BOM Lines |  | 1 | 91 | 1 | 100%
All |  | Filter lists by Buyer: RFQ, SIF |  |  | 91 | 3 | 100%
RFQ | 4 | Optional Button when sending new request: Aero or Auto. | 14 | 1 |  | 1 | 100%
All | 3 | Allow filtering data by these part numbers: Finished Good (From BOM), Capsonic PN (From BOM), Manufacture PN(From drawingos or BOM) | 35 | 1 |  | 2 | 100%
Re-schedule or New:
BOM | 3 | Filter BOM list by Buyer | 94 | 1 | 94 | 1 | 100%
Supplier | 3 | Content inside emails for Vendors. | 94 | 1 | 94 | 1 | 100%
RFQ | 3 | Choose vendor filtering by its Commodity. | 94 | 1 | 94 | 5 | 100%
BOM | 3 | Calculate EAU for BOM automatically, pulled from SIF | 95 | 1 | 98 | 1 | 100%
System | 3 | Standardize names | 95 | 1 | 99 | 1 | 100%
SIF | 3 | Create SIF Detail | 95 | 1 | 106 | 1 | 100%
All | 3 | Validate forms. | 95 | 1 | 14 | 3 | 90% | bar: PERIODS 14 to PERIODS 15
RFQ | 3 | Multiple Part Numbers to RFQ, handle manufacture P/N and Capsonic P/N columns | 98 | 2 | 133 | 3 | 100%
Supplier | 3 | Ranking functionality. | 269 | 7
Reports | 3 | Develop all reports. Begin with necessaries and in HTML format. | At the end |  |  |  | 20%
System | 1 | User's Manual | 119 | 5
System | 1 | Technical Documentation | 126 | 5
New after using the system:
| 5 | Handle compatibility view in Internet Explorer |  |  | 99 | 1 | 100%
| 5 | Re-order steps of instructions in RFQ after standardization and movement of some fields location. |  |  | 99 | 1 | 100%
| 5 | Report to Sales is not shwoing all BOM lines |  |  | 100 | 1 | 100%
| 5 | Change Dissmised to No Quote |  |  | 100 | 1 | 100%
| 5 | Buyer should be able to update RFQ |  |  | 100 | 1 | 100%
| 5 | Delete RFQ |  |  | 101 | 1 | 100%
| 5 | Force EAU field to be filled in so Purchasing cannot send out RFQ without EAUs |  |  | 101 | 1 | 100%
| 5 | Status of BOM Line should be change to In Progress when RFQ(s) are sent. |  |  | 101 | 1 | 100%
| 4 | RFQ Summary: Pull Total Cost for update it in BOM Line. |  |  | 102 | 1 | 100%
| 4 | Allow Buyers to create manually RFQ (without submitting to Vendor) |  |  | 102 | 1 | 100%
| 4 | Add column for know if SIF was created or imported |  |  | 105 | 1 | 100%
| 3 | Add titles along the different screens |  |  | 105 | 1 | 100%
| 3 | Hide Cost field in BOM |  |  | 105 | 1 | 100%
| 1 | Remove BOMDetailKey when selecting a BOM Line in RFQSummary |  |  | 105 | 1 | 100%
| 1 | Remove columns from Suppliers list (Manuf. Loc., Ship Loc., Quoted Currency) |  |  | 105 | 1 | 100%
| 1 | Remove title Proyected Annual Volume when sending new RFQ |  |  | 105 | 1 | 100%
| 1 | Prevent overlapping in RFQ Summary with columns and Header info. |  |  | 106 | 1 | 100%
| 3 | Not apply automatically EAU for all BOM lines when they have been processed |  |  | 107 | 1 | 100%
| 3 | Pull Tooling field from RFQ to RFQ summary. |  |  | 107 | 1 | 100%
| 2 | Prevent from exit a page every time we save something |  |  | 107 | 6 | 100%
| 2 | Remove Multiview controls, instead, use normal webpages. |  |  | 107 | 6 | 100%
| 3 | RFQs inside BOM |  |  | 109 | 15 | 100%
| 1 | Re-sent RFQ |  |  | 113 | 1 | 100%
|  | Add last date send column for RFQs |  |  | 114 | 1 | 100%
| 3 | Add cavitation and material fields to RFQ Form. |  |  | 114 | 1 | 100%
|  | Allow to change Vendor's email when resending RFQ. |  |  | 115 | 1 | 100%
| 1 | Delete BOM from SIF list. | 116 | 1 | 116 | 1 | 100%
|  | Remove EAU validation from BOM Form |  |  | 120 | 1 | 100%
|  | Allow edit RFQ about Buyer fields. |  | 2 | 123 | 6 | 100%
|  | Session timeout increased. |  |  | 130 | 1 | 100%
|  | Sales comments in BOM |  |  | 130 | 1 | 100%
|  | Handle 3 digits for decimal's precision. |  |  | 133 | 1 | 100%
|  | New Lead Times requested by Seth. |  |  | 135 | 1 | 100%
|  | Create RFQ per each EAU pulled from SIF requested by Seth and Tom | 116 | 1 | 135 | 1 | 100%
|  | Advance Purchasing Recommendation report |  |  | 136 | 2 | 100%
|  | Report to Sales (copy) showing all RFQs |  |  | 140 | 1 | 100%
Tasks that will be treated as improvements. (After system's basics work)
| 5 | Add Buyer contact that created an RFQ inside form |  |  | 245 | 1 | 100%
| 5 | Separate RFQ Summaries by EAUs (Show EAU in RFQ Summary) |  |  | 240 | 1 | 100%
| 5 | Attachments in IE8 |  |  | 233 | 1 | 100%
| 4 | Add Vendor's phone in RFQ form |  |  | 245 | 1 | 100%
| 4 | UM in Report to Sales |  |  | 171 | 1 | 100%
| 5 | to be able to quote some component that was before estimated, but not remove the estimated information | 256 | 1 | 260 | 1 | 100%
| 5 | Don’t delete records, just set to inactive | 256 | 4 | 260 | 2 | 100%
| 5 | RFQ Number and Component PN inside email | 259 | 1 |  |  | 0%
| 4 | Manfucaturing Location and Ship fields belongs to RFQ as well | 260 | 1 |  |  | 0%
| 4 | UM in RFQ Summary | 260 | 1 |  |  | 0%
| 4 | Know the last email used when a RFQ was sent | 260 | 1 |  |  | 0%
| 4 | Export Sales Report component processed without RFQ | 261 | 1 |  |  | 0%
| 3 | Open RFQs from RFQ summary | 261 | 1 |  |  | 0%
| 3 | Leyend when sending RFQ depending if Aerospacial or Automotive | 262 | 1 |  |  | 0%
| 3 | Days/Wks for Lead Times | 262 | 2 |  |  | 0%
| 3 | Add Prototype Tooling and Prototype quantity to RFQ Summary | 263 | 1 |  |  | 0%
| 3 | PPAP/FAIR cost | 263 | 1 |  |  | 0%
| 3 | Filter by dates SIF list | 266 | 1 |  |  | 0%
| 3 | To be able to quote some component that was before estimated, but not remove the estimated information | 266 | 2 |  |  | 0%
| 3 | Be able to Select RFQ as a winner in BOM | 268 | 1 |  |  | 0%
| 3 | 5 decimal places in RFQ form | 268 | 1 |  |  | 0%
| 3 | Move old data of Lead Times to new columns | 269 | 1 |  |  | 0%
| 2 | Use FS Commodities. | 276 | 5 |  |  | 0%
| 2 | Handle manual process by attaching in SIF | 281 | 5 |  |  | 0%
| 2 | Remove from SIF List column Cost Model Loc | 287 | 1 |  |  | 0%
| 2 | Draft when sending a RFQ. | 287 | 3 |  |  | 0%
| 2 | Brand and Revision level uppercase | 289 | 1 |  |  | 0%
| 2 | Close RFQ after hiting save or cancel | 290 | 1 |  |  | 0%
| 2 | Export reports to Excel format | 290 | 5 |  |  | 0%
| 2 | Increase Inquiry Number font size inside BOM | 294 | 1 |  |  | 0%
| 1 | Do not allow a vendor to fill out a survey more than once. | 295 | 1 |  |  | 0%
| 1 | Status Progress as column in SIF list. | 296 | 1 |  |  | 0%
| 1 | Page inside emails | 296 | 1 |  |  | 0%
System | 1 | Static Headers for Tables | 297 | 1 |  |  | 0%
| 1 | See issue with NDA | 298 | 1 |  |  | 0%
RFQ | 1 | Implement expiration RFQs functionality. (Due date, close, blocked, extend them). | 301 | 1 |  |  | 0%
System | 1 | Style webpage. | 302 | 4 |  |  | 50%
Created By | New tasks added since May
Martha | 3 | Buttons for check all items or uncheck them in BOM screen.
Martha | 5 | Highlight rows already Selected/Awarded in screen that opens RFQ Summary |  |  | 242 | 1 | 100%
White and Martha | 5 | Multiple EAUs in one RFQ: |  |  | 223 | 19 | 100%
White and Martha | 5 | ---HTML Report with new structure of EAUs |  |  | 241 | 1 | 100%
White and Martha | 5 | ---RFQ Summary with new structure of EAUs |  |  | 238 | 3 | 100%
White and Martha | 5 | ---RFQ Form compatible with IE8 |  |  | 240 | 1 | 100%
White and Martha | 5 | ---Attachments new structure |  |  | 231 | 3 | 100%
White and Martha | 5 | ---RFQ Vendor side working new structure |  |  | 235 | 3 | 100%
White and Martha | 5 | ---Formulas done in new structure of RFQDetail |  |  | 231 | 1 | 100%
White and Martha | 5 | ---New RFQDetail with new Excel spreadsheet style |  |  | 223 | 3 | 100%
White and Martha | 5 | ---New structure to Database |  |  | 223 | 3 | 100%
White and Martha | 5 | ---Saving RFQEAV when creating new RFQs |  |  | 217 | 1 | 100%
White | 5 | Move MOQ field to each EAU in RFQForm |  |  | 237 | 1 | 100%
Alfredo | 5 | Add date validation to my validator component reusable |  |  | 240 | 1 | 100%
Alfredo | 5 | Attachments working in IE8 |  |  | 233 | 1 | 100%
Everyone | 5 | New email sender in order to prevent mails being junked |  |  | 212 | 1 | 100%
Alfredo | 5 | Upgrade project from VS2008 to VS2010 |  |  | 210 | 1 | 100%
White | 5 | New fields in RFQ form, specified in email by Magdeline | 254 | 2 | 256 | 4 | 100%
Seth and Lorie | 3 | Be able to combine SIFs and quote unique components summarizing qty |  | 20
Martha | 3 | Edit "Report to Sales" in order to have these columns: Supplier Comments, Supplier Exceptions, Purchasing Status |  | 1
White | 3 | Change email content as specify by Magdeline's email |  | 1
White | 3 | Add Drawing Revision to BOM screen |  | 1
Martha | 3 | Add Prototype Tooling field to Report to Sales |  | 1
Martha | 3 | Add LN column to BOM Screen |  | 1
Created By | Not programmed
Martha |  | Add UM to Sales DB so then, it can be imported to APQM |  |  | 267 | 2 | 100%
Note on Q13: Transactions in SalesDB2APQM done.
Note on AA13: Transactions in RFQ Form done.
Note on CL13: Transactions done for APQM
Note on DK103: Designed for allow 5 RFQs
Note on DX108: Holyday